## Cover
Sample Compliance Checklist
Disclaimer: This information is provided for general guidance purposes only and does not constitute legal or professional advice. Compliance requirements may vary depending on the scope, location, and nature of the works. You should always verify specific obligations with the relevant competent authorities before commencing any refurbishment, renovation, or fit-out project.
In Ireland, further details and official guidance can be obtained from:
• Building Control Regulations (BCAR) – Local Authority Building Control Office and the Building Control Management System (BCMS): https://www.localgov.ie/en/building-control
• Disability Access Certificates (DAC) – Local Authority Planning and Building Control Departments, Technical Guidance Document Part M: https://www.gov.ie/en/publication/5c7a11-building-regulations/
• Fire Safety Certificates – Local Authority Fire Service, Technical Guidance Document Part B: https://www.gov.ie/en/publication/5c7a11-building-regulations/
• Crib 5 Material Compliance – Testing to BS 7177 / BS 5852 standards through accredited laboratories; guidance via the National Standards Authority of Ireland (NSAI): https://www.nsai.ie/

## Sample Checklist
Category | Checklist for Complete Refurb/Renovation/Fit-Out
BCAR (Building Control Amendment Regulations) | 1. Appoint Assigned Certifier before starting design
2. Prepare and submit Commencement Notice via BCMS
3. Upload Design Certificate, Builder Undertaking, and Inspection Plan
4. Ensure all drawings meet Building Regulations
5. Coordinate with structural engineers and architects
6. Maintain inspection records throughout works
7. Submit Completion Certificate before occupancy
DAC (Disability Access Certificate) | 1. Engage an access consultant during concept design
2. Ensure all public areas meet Part M standards (widths, turning circles)
3. Provide accessible guestrooms and bathrooms per regulations
4. Install compliant ramps, lifts, and handrails
5. Verify signage is tactile and at correct heights
6. Include accessible WC facilities in all public-use areas
7. Submit DAC application to local authority before construction starts
Fire Safety Certificate | 1. Engage fire safety engineer at concept stage
2. Calculate occupancy load for all spaces
3. Design compliant means of escape (exits, stairs, widths)
4. Ensure compartmentation between rooms and functional spaces
5. Design and specify compliant fire detection/alarm systems
6. Specify emergency lighting to relevant standards
7. Obtain Fire Safety Certificate from local authority before works commence
Crib 5 Material Compliance | 1. List all upholstered items in public and guest areas
2. Specify fabrics and foams tested to BS 7177 / BS 5852 (Crib 5)
3. Obtain compliance certificates from all suppliers
4. Keep compliance certificates in project file for inspections
5. Ensure replacement furniture/fabrics also meet Crib 5
6. Train procurement team to request proof of compliance
7. Verify all delivered items match approved specifications